## UI Test Plan
Food Rescue UI Test Plan
Prepared by Haoxuan Liu. 12 October 2026. Planned cases, not execution evidence.
Total cases | 68 | Pass | 0 | Fail | 0 | Not Run | 68
Fill amber result fields after testing. Use Blocked if the screen or environment is unavailable.
ID | Screen | Role | Priority | Fix owner | Test case | Preconditions / data | Steps | Expected result | Status | Actual result | Evidence path / link | Defect ID | Test date / build
UI-001 | Login | All | High | Ree | Donor login | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Open login. 2. Enter donor credentials. 3. Submit. | Donor portal opens. Correct user ID and DONOR role are stored. | Not Run
UI-002 | Login | All | High | Ree | Recipient login | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Enter approved recipient credentials. 2. Submit. | Recipient portal opens with the correct organisation ID. | Not Run
UI-003 | Login | All | High | Ree | Admin login | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Enter admin credentials. 2. Submit. | Admin portal opens. Correct ADMIN role is returned. | Not Run
UI-004 | Login | All | High | Ree | Incorrect password | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Enter a known email and wrong password. 2. Submit. | Stay on login. Display API error: Invalid email or password. | Not Run
UI-005 | Login | All | High | Ree | Unknown email | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Enter an unregistered email and any password. 2. Submit. | Stay on login. Display Invalid email or password. | Not Run
UI-006 | Login | All | High | Ree | Empty credentials | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Leave both fields blank. 2. Submit. | Required-field feedback appears. No authenticated session is created. | Not Run
UI-007 | Login | All | High | Ree | Logout | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Log in. 2. Click logout. 3. Try opening a role page. | Stored user is cleared. Login is required again. | Not Run
UI-008 | Login | All | High | Ree | Role route protection | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Log in as donor. 2. Navigate directly to recipient and admin URLs. | Frontend prevents access to the other role views. This does not prove backend authorisation. | Not Run
UI-009 | Login | All | Medium | Ree | Email spaces and case | Backend running. Known donor, approved recipient and admin accounts exist. | 1. Try the same email with spaces. 2. Try altered case. | Record behaviour and API response. UI shows any API error. Normalisation rule needs team confirmation. | Not Run
UI-010 | Register | Public | High | Ree | Register donor | Use unique test emails. Do not reuse emails from an earlier run. | 1. Choose Donor. 2. Fill valid required fields. 3. Submit. 4. Log in. | One DONOR user is created and can log in. | Not Run
UI-011 | Register | Public | High | Ree | Register recipient | Use unique test emails. Do not reuse emails from an earlier run. | 1. Choose Recipient organisation. 2. Fill required fields. 3. Submit. | One RECIPIENT_ORG user is created with PENDING verification. | Not Run
UI-012 | Register | Public | High | Ree | Duplicate email | Use unique test emails. Do not reuse emails from an earlier run. | 1. Register using an existing email. 2. Submit. | No second user is created. API error is shown. | Not Run
UI-013 | Register | Public | High | Ree | Missing required fields | Use unique test emails. Do not reuse emails from an earlier run. | 1. Leave each required field empty in turn. 2. Submit. | Field validation prevents incomplete registration or displays API validation error. | Not Run
UI-014 | Register | Public | High | Ree | Invalid email | Use unique test emails. Do not reuse emails from an earlier run. | 1. Enter an invalid email format. 2. Submit. | Record validation behaviour. Invalid email should be rejected by the UI; capture any backend acceptance as a known gap. | Not Run
UI-015 | Register | Public | High | Ree | Public roles only | Use unique test emails. Do not reuse emails from an earlier run. | 1. Inspect the role selector. 2. Register through the normal UI. | Only Donor and Recipient organisation are offered. ADMIN is never a public option. | Not Run
UI-016 | Post donation | Donor | High | Yeyun | Valid donation | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Enter title, category, positive quantity and required details. 2. Submit. 3. Open donor list. | 201 creates one AVAILABLE donation. It belongs to the logged-in donor and appears in their list. | Not Run
UI-017 | Post donation | Donor | High | Yeyun | Missing required field | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Omit each required field in turn. 2. Submit. | Clear validation feedback. No incomplete donation is created. | Not Run
UI-018 | Post donation | Donor | High | Yeyun | Zero quantity | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Enter quantity 0. 2. Submit. | UI validation or API 400 prevents creation. API error is visible. | Not Run
UI-019 | Post donation | Donor | High | Yeyun | Negative quantity | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Enter quantity -1. 2. Submit. | UI validation or API 400 prevents creation. | Not Run
UI-020 | Post donation | Donor | High | Yeyun | Category values | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Open category selector. 2. Select a category. 3. Submit. | Options map to the API category enums listed in Run Guide. | Not Run
UI-021 | Post donation | Donor | High | Yeyun | Collection time conversion | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Enter a local pickup deadline. 2. Submit. 3. Compare request and displayed time. | ISO-8601 instant represents the intended Adelaide time. Display does not shift the deadline unexpectedly. | Not Run
UI-022 | Post donation | Donor | High | Yeyun | Donor identity | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Log in as donor B. 2. Post a donation. 3. Inspect request and lists. | Request uses donor B ID rather than hard-coded donorId=1. | Not Run
UI-023 | Post donation | Donor | Medium | Yeyun | Repeated submit | Logged-in donor. Capture returned IDs. Use future collection deadlines. | 1. Fill valid data. 2. Double-click Submit rapidly. | One donation is created. Button/loading state prevents duplicate requests. | Not Run
UI-024 | Donor list and stats | Donor | High | Yeyun | Own donation list | Donor has AVAILABLE, RESERVED and COLLECTED donations. | 1. Open donor donations. 2. Compare with donor API list. | Only the logged-in donor list is displayed, with dates and correct statuses. | Not Run
UI-025 | Donor list and stats | Donor | High | Yeyun | Cancel available donation | Donor has AVAILABLE, RESERVED and COLLECTED donations. | 1. Select an AVAILABLE item. 2. Cancel it. 3. Refresh. | Cancellation succeeds. The item is no longer available to reserve. | Not Run
UI-026 | Donor list and stats | Donor | High | Yeyun | Cancel restrictions | Donor has AVAILABLE, RESERVED and COLLECTED donations. | 1. Inspect RESERVED and COLLECTED items. | Cancel action is offered only for AVAILABLE items. | Not Run
UI-027 | Donor list and stats | Donor | Medium | Yeyun | Donor stat cards | Donor has AVAILABLE, RESERVED and COLLECTED donations. | 1. Open stat cards. 2. Compare with user stats API. | Counts match the donor response. If this optional feature is cut, record N/A with reason. | Not Run
UI-028 | Browse donations | Recipient | High | Ree | Available list | Approved recipient logged in. Available, reserved and expired donations exist. | 1. Open Browse. 2. Compare with available API list. | Displays AVAILABLE items. RESERVED, COLLECTED and EXPIRED items are excluded. | Not Run
UI-029 | Browse donations | Recipient | Medium | Ree | Category filter | Approved recipient logged in. Available, reserved and expired donations exist. | 1. Select a category. 2. Clear filter. | Selected category matches displayed items. Clear restores all available items. If cut, record N/A. | Not Run
UI-030 | Browse donations | Recipient | Medium | Ree | Empty list | Approved recipient logged in. Available, reserved and expired donations exist. | 1. Use an empty data set or category. 2. Open Browse. | Readable empty state appears with no broken cards. | Not Run
UI-031 | Browse donations | Recipient | High | Ree | Expiry refresh | Approved recipient logged in. Available, reserved and expired donations exist. | 1. Create an available item with a past deadline through test setup. 2. Wait about 70 seconds. 3. Refresh. | Expired item disappears from Browse after the expiry job runs. | Not Run
UI-032 | Reserve dialog | Recipient | High | Ree | Reserve available donation | Approved recipient and AVAILABLE donation exist. Prepare a pending recipient as well. | 1. Open donation. 2. Choose valid pickup time. 3. Confirm. | 201 creates PENDING reservation for the logged-in org. Donation becomes RESERVED and leaves Browse. | Not Run
UI-033 | Reserve dialog | Recipient | High | Ree | Pending approval banner | Approved recipient and AVAILABLE donation exist. Prepare a pending recipient as well. | 1. Log in as PENDING recipient. 2. Open Browse and attempt reserve. | Approval banner is visible. Reservation is blocked and any API approval error is shown. | Not Run
UI-034 | Reserve dialog | Recipient | High | Ree | Already reserved item | Approved recipient and AVAILABLE donation exist. Prepare a pending recipient as well. | 1. Open same item in two sessions. 2. Reserve in first. 3. Reserve in stale second session. | Second attempt fails without duplicate reservation. API error is displayed and list can refresh. | Not Run
UI-035 | Reserve dialog | Recipient | Medium | Ree | Close reserve dialog | Approved recipient and AVAILABLE donation exist. Prepare a pending recipient as well. | 1. Open dialog. 2. Close without confirming. | No reservation request is sent. Donation remains AVAILABLE. | Not Run
UI-036 | Reserve dialog | Recipient | High | Ree | Repeat reserve click | Approved recipient and AVAILABLE donation exist. Prepare a pending recipient as well. | 1. Submit reservation twice rapidly. | Only one active reservation exists. API errors are not hidden. | Not Run
UI-037 | Reserve dialog | Recipient | High | Ree | Pickup time display | Approved recipient and AVAILABLE donation exist. Prepare a pending recipient as well. | 1. Choose local pickup time. 2. Reserve. 3. Open My reservations. | Stored instant and displayed local time match the selection. | Not Run
UI-038 | My reservations | Recipient | High | Ree | Own reservation list | Recipient A and B have separate reservations. Use a fresh item for cancel and collect tests. | 1. Log in as A. 2. Open My reservations. 3. Compare recipient API list. | Only A reservations are shown with correct donation, pickup time and status. | Not Run
UI-039 | My reservations | Recipient | High | Ree | Mark collected | Recipient A and B have separate reservations. Use a fresh item for cancel and collect tests. | 1. Select an active reservation. 2. Mark collected. 3. Refresh. | Reservation and donation are COLLECTED. Donation collectedAt is populated. | Not Run
UI-040 | My reservations | Recipient | High | Ree | Cancel reservation | Recipient A and B have separate reservations. Use a fresh item for cancel and collect tests. | 1. Select an active reservation. 2. Cancel. 3. Refresh Browse. | Reservation becomes CANCELLED. Donation becomes AVAILABLE and is visible in Browse. | Not Run
UI-041 | My reservations | Recipient | High | Ree | Reserve after cancel | Recipient A and B have separate reservations. Use a fresh item for cancel and collect tests. | 1. Cancel a reservation. 2. Reserve the same donation again. | New reservation succeeds. Old row stays CANCELLED. Only one active reservation exists. | Not Run
UI-042 | My reservations | Recipient | Medium | Ree | Empty reservations | Recipient A and B have separate reservations. Use a fresh item for cancel and collect tests. | 1. Log in with an org that has no reservations. 2. Open list. | Clear empty state appears. | Not Run
UI-043 | Report a problem | Recipient | High | Ree | Submit incident | Recipient logged in. Donation exists. Use a collected dairy donation for the use-by case. | 1. Open Report a problem for a donation. 2. Enter description and valid severity. 3. Submit. | 201 creates OPEN incident for the correct donation and reporter. Confirmation is visible. | Not Run
UI-044 | Report a problem | Recipient | High | Ree | Severity options | Recipient logged in. Donation exists. Use a collected dairy donation for the use-by case. | 1. Open severity selector. 2. Submit each option using separate incidents. | MINOR, MODERATE and SEVERE map correctly to requests. | Not Run
UI-045 | Report a problem | Recipient | High | Ree | Blank description | Recipient logged in. Donation exists. Use a collected dairy donation for the use-by case. | 1. Leave description blank. 2. Submit. | Validation prevents submission or API 400 error is shown. | Not Run
UI-046 | Report a problem | Recipient | High | Ree | Dairy use-by mismatch | Recipient logged in. Donation exists. Use a collected dairy donation for the use-by case. | 1. Select collected dairy item. 2. Describe mismatch between communicated and printed use-by dates. 3. Submit. | Incident preserves the description, severity, donation reference and reporter for admin follow-up. | Not Run
UI-047 | Report a problem | Recipient | High | Ree | Reporter and donor details | Recipient logged in. Donation exists. Use a collected dairy donation for the use-by case. | 1. Submit an incident. 2. Inspect admin detail and API response. | Correct reporter, donor ID/name/organisation, donation title and reported timestamp are available. | Not Run
UI-048 | Report a problem | Recipient | High | Ree | Donor cannot flag through UI | Recipient logged in. Donation exists. Use a collected dairy donation for the use-by case. | 1. Log in as donor. 2. Inspect donation actions and recipient report route. | No Flag a problem action is offered. Recipient report route is protected. | Not Run
UI-049 | Report a problem | Recipient | Medium | Ree | Uncollected or pending reporter | Recipient logged in. Donation exists. Use a collected dairy donation for the use-by case. | 1. Try reporting as pending org. 2. Try a donation the org never collected. | Record actual behaviour. Backend currently allows both. Confirm permission policy with Chenlu/Anil rather than invent a rule. | Not Run
UI-050 | Admin dashboard | Admin | High | Yeyun | Dashboard counts | Admin logged in. Prepare incidents and pending recipients. | 1. Open dashboard. 2. Compare every displayed count with stats API. | Cards match API values, including unresolved OPEN plus UNDER_REVIEW incidents. | Not Run
UI-051 | Admin dashboard | Admin | High | Yeyun | Incident highlight | Admin logged in. Prepare incidents and pending recipients. | 1. Prepare at least one unresolved incident. 2. Open dashboard. 3. Resolve all and refresh. | Open-incident indicator is highlighted above 0 and clears when count is 0. | Not Run
UI-052 | Recipient approvals | Admin | High | Yeyun | Pending list | At least two PENDING recipient organisations exist. | 1. Open approvals. 2. Compare pending-verifications response. | Pending organisations are listed correctly. | Not Run
UI-053 | Recipient approvals | Admin | High | Yeyun | Approve organisation | At least two PENDING recipient organisations exist. | 1. Approve a pending org. 2. Refresh. 3. Log in as that recipient and reserve. | PUT updates verificationStatus to APPROVED. Org leaves pending list and can reserve. | Not Run
UI-054 | Recipient approvals | Admin | High | Yeyun | Reject organisation | At least two PENDING recipient organisations exist. | 1. Reject a separate pending org. 2. Inspect response. 3. Try reserving as it. | Verification status updates to the documented rejected state. Org cannot reserve. Capture request/error on failure. | Not Run
UI-055 | Recipient approvals | Admin | Medium | Yeyun | No pending organisations | At least two PENDING recipient organisations exist. | 1. Process all pending orgs. 2. Refresh approvals. | Clear empty state, with no stale approval actions. | Not Run
UI-056 | Admin incidents | Admin | High | Yeyun | Incident list and filters | OPEN, UNDER_REVIEW and RESOLVED incidents exist. | 1. Open incidents. 2. Select each status. 3. Compare API results. | Filter results and status labels are accurate. Donor and reporter details are visible. | Not Run
UI-057 | Admin incidents | Admin | High | Yeyun | Move under review | OPEN, UNDER_REVIEW and RESOLVED incidents exist. | 1. Select OPEN incident. 2. Mark under review. 3. Refresh. | Status becomes UNDER_REVIEW. Unresolved count still includes this incident. | Not Run
UI-058 | Admin incidents | Admin | High | Yeyun | Resolve with notes | OPEN, UNDER_REVIEW and RESOLVED incidents exist. | 1. Open incident. 2. Enter resolution notes. 3. Resolve. 4. Refresh. | Status becomes RESOLVED. Notes and resolvedAt persist. Unresolved count decreases. | Not Run
UI-059 | Admin incidents | Admin | High | Yeyun | Resolve failure feedback | OPEN, UNDER_REVIEW and RESOLVED incidents exist. | 1. Attempt resolve with invalid/missing required data. 2. Inspect UI and response. | UI displays validation/API error and does not falsely show resolution success. Record blank-note policy if API accepts it. | Not Run
UI-060 | Admin incidents | Admin | Medium | Yeyun | Report date range | OPEN, UNDER_REVIEW and RESOLVED incidents exist. | 1. Choose range containing incidents. 2. Generate report. 3. Compare report API. | Totals, severity/status grouping and included incidents match API. Optional report may be N/A if cut. | Not Run
UI-061 | Admin incidents | Admin | Medium | Yeyun | Empty period and invalid dates | OPEN, UNDER_REVIEW and RESOLVED incidents exist. | 1. Choose a period with no incidents. 2. Try invalid dates. | Empty period shows total 0. Invalid date submission is blocked or API error is displayed. | Not Run
UI-062 | Admin incidents | Admin | Low | Yeyun | Print report | OPEN, UNDER_REVIEW and RESOLVED incidents exist. | 1. Generate period report. 2. Click Print. 3. Inspect print preview. | Readable report prints without navigation covering content. If report feature is cut, record N/A. | Not Run
UI-063 | Shared UI and full flow | All | High | Ree / Yeyun | Loading and request failure | Run against the real backend in the browser. Record versions and screenshots. | 1. Throttle network on each screen. 2. Load it. 3. Stop backend and retry. | Loading state is visible. Failure has readable feedback and retry. No infinite spinner or false success. | Not Run
UI-064 | Shared UI and full flow | All | High | Ree / Yeyun | Console errors | Run against the real backend in the browser. Record versions and screenshots. | 1. Open DevTools Console. 2. Execute each role flow. | No uncaught errors occur. Save console evidence for failures. | Not Run
UI-065 | Shared UI and full flow | All | High | Ree / Yeyun | Full donor-recipient loop | Run against the real backend in the browser. Record versions and screenshots. | 1. Donor posts. 2. Approved recipient browses and reserves. 3. Recipient collects. 4. Admin verifies counts. | Same donation completes the full browser flow. IDs and statuses agree with API responses. | Not Run
UI-066 | Shared UI and full flow | All | High | Ree / Yeyun | Full incident loop | Run against the real backend in the browser. Record versions and screenshots. | 1. Recipient reports problem. 2. Admin marks under review. 3. Admin resolves with notes. 4. Recipient refreshes. | Incident and resolution persist. Role views and dashboard show updated state. | Not Run
UI-067 | Shared UI and full flow | All | Medium | Ree / Yeyun | Notifications if present | Run against the real backend in the browser. Record versions and screenshots. | 1. Reserve, collect, flag, resolve and approve. 2. Inspect relevant bell counts. 3. Mark read. | Built notification UI matches unread API. Cancellation/new-donation/expiry notifications are not implemented. If UI omitted, record N/A. | Not Run
UI-068 | Shared UI and full flow | All | Medium | Ree / Yeyun | Narrow screen and keyboard | Run against the real backend in the browser. Record versions and screenshots. | 1. Test narrow browser width. 2. Tab through forms. 3. Submit using keyboard. | Required controls remain usable. Labels, focus and errors are readable. | Not Run

## Run Guide
Execution guide
Topic | Instructions / source
Scope | Day 6 task: UI cases for login, register, post donation, browse, reserve, My reservations, report a problem and admin screens.
How to run | Use the real backend and the current frontend. Execute each numbered case. Fill Status, Actual result, Evidence, Defect ID and build/date.
Test status | Not Run: not executed. Pass: expected result observed with evidence. Fail: mismatch. Blocked: prerequisite or screen missing. N/A: removed optional feature, with reason.
Environment record | Record browser/version, frontend branch and commit, backend branch and commit, run date and API base URL in Actual result for the first executed case or evidence log.
Setup | Start backend from pom.xml folder. Run seed-demo-data.ps1 where available. Create donor A/B, approved recipient A/B, pending recipient and admin. Record actual IDs rather than assuming ID 1.
Database | H2 data resets on backend restart. Recreate data and recapture IDs. Use fresh donations for destructive collect/cancel cases.
Dates | Use future collection deadlines and pickup times. Compare Adelaide local time with ISO-8601 instants. Do not reuse expired hard-coded dates.
UI evidence | Save screenshot and relevant request/response under docs/test-evidence. Example: docs/test-evidence/ui/2026-10-12/UI-001.png. Use unique run folders.
Failures | Create defect ID, severity, reproduction steps, expected vs actual, owner and status in the existing defect log. Attach screenshot plus request/response. Retest against the fixed build.
Owners | Ree: login, registration and recipient screens. Yeyun: donor/admin screens. Anil: backend errors. Chenlu: unclear incident permissions and acceptance criteria. Haoxuan: execution/evidence.
Authentication limit | Frontend role guards must be tested. Backend currently returns no token and endpoints are open. UI route protection does not establish backend security.
Incident permission limit | Backend permits pending recipients and reports on uncollected donations. Treat permission policy as an open question for Chenlu/Anil. Do not mark unconfirmed rules as passed.
Client incident fields | Current client response requests report time, donation reference/donor/item, description, severity, reporter role/name/org and optional notes. Client screenshot is partial: do not infer unseen answers.
Optional features | Category filter, donor cards, period report and notification UI may be cut. Record N/A with an agreed reason rather than Pass. Keep core flows and recipient approvals.
Category enums | FRESH_PRODUCE, BAKERY, DAIRY, MEAT_AND_SEAFOOD, PANTRY_AND_DRY_GOODS, PREPARED_MEALS, BEVERAGES, OTHER.
Severity / status | Severity: MINOR, MODERATE, SEVERE. Incident status: OPEN, UNDER_REVIEW, RESOLVED.
Submit location | Use the existing backend branch. Save this workbook under docs. No new branch or PR for this upload.
Source 1 | 10_Day_Team_Plan(1).pdf, Haoxuan task table, page 3, 12 October row. Later team instruction overrides its original branch/PR rule.
Source 2 | API_DOCUMENTATION.md and API_Testing_Handoff.md supplied 9 October 2026. Recheck endpoint changes against the current build before execution.
Source 3 | IMG_5695.png, host incident-record response. Visible first-question fields only.
Preparation limit | Frontend screens were not inspected or executed during plan authoring. Cases specify planned acceptance checks, not observed test results.